## Sheet1
| Week Start | 2019-11-25 | 2019-12-02 | 2019-12-09 | 2019-12-16
User Story | % Complete | Week 1 | Week 2 | Week 3 | Week 4
As a customer I need to log on to a website including the following sections Introduction portal, Explore, Exhibition Spaces, Special Events, Visit and booking page. | 0% | Build Time |  |  | Debug & Troubleshoot
As a customer I would like to see a calender with the different events and the opening times so I can plan a visit | 0% | Build Time
As a custormer I want to know the prices for tickets including OAP tickets and children tickets. | 0% |  | Build Time
As a science enthasusit I can read a summary of each of the exhibits in the museaum so I can decide to come when a new exhibtion comes to the museum | 0% |  | Build Time
As a custormer I would like to buy tickets for my group so I can get a reduced price. | 0% |  | Build Time
As a wheel chair using custormer I need to check if the museum has facilites for me and that I can have a tour guide that will push my chair. | 0% |  |  | Build Time
As a student with restricted access to science resources I can see online what science events show practical demonstrations | 0% |  |  |  | Build Time
As a student with restricted access to science resources how I can obtain prior knowledge of the practical demonstations. | 0% |  |  |  | Build Time