## Sheet1
| People Assigned for the deliverables | [5 empty] | 2019-11-17 | 2019-11-24 | 2019-12-01 | 2019-12-08 | 2019-12-15 | 2019-12-22 | 2019-12-29 | 2020-01-05 | 2020-01-12 | 2020-01-19 | 2020-01-26 | 2020-02-02
User Story | Local Lead 1 | Local Lead 2 | Global Lead | Copy writer | Scrum manager | % Complete | Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 6 | Week 7 | Week 8 | Week 9 | Week 10 | Week 11 | Week 12
As a customer I need to log on to a website including the following Contact us, About us, Online-Shop and Brand recommended recipes. | [5 empty] | 0% | 2019-11-17: Build Time; 2019-12-15: Debug & Troubleshoot; 2019-12-29: Buffer week
As a scrum manager I will set up a company account with google documents to share documents and set up gmail accounts for all the development team. | [5 empty] | 0% | bar: 2019-11-17
As the bank manager I will have to check and authorise the responsive payment form so that Loftus frukt og saft can have an company bank account that all trades will come through. | [5 empty] | 0% | bar: 2019-11-24 to 2019-12-01
As a Norwegian speaking customer, I want to fill out an order form for multiple 1L bottles so that I can buy a gift on my credit card for myself and my friends/family. | [5 empty] | 0% | bar: 2020-01-05 to 2020-01-12
As a large retail customer I want to order a starter pack so that I can try out "Lofthus frukt og saft" for my business | [5 empty] | 0% | bar: 2020-01-12
As a large retail customer I want to give feedback on the product so that the next purchase is too my requirements. | [5 empty] | 0% | bar: 2020-01-19
As a large retail customer I want a loyalty code with "Lofthus frukt og saft" after 3 purchases to reward me business. | [5 empty] | 0% | bar: 2020-01-19
As an English speaking, customer, I want to fill out an order form for multiple large 1L bottles so that I can buy a gift on my credit card for myself and my friends/family. | [5 empty] | 0% | bar: 2020-01-26